## Work Plan
Task | Start Date | Days to complete | Completion Date
Data Cleaning | 2016-10-06 | 7 | 2016-10-12
Documentation | 2016-10-06 | 70 | 2016-12-14
R Script Draft | 2016-11-09 | 4 | 2016-11-12
R Script Final | 2016-11-13 | 4 | 2016-11-16
R Plot Draft | 2016-11-17 | 5 | 2016-11-21
R Plot Final | 2016-11-22 | 9 | 2016-11-30
Prepare Final Presentation | 2016-12-01 | 14 | 2016-12-14

## Sheet1
Job to be done | Responsible Person
Data Cleaning Rank favorable countries based on macroeconomic factors | Tu
Data Cleaning Rank favorable countries based on human capital factors | Prerak
Data Cleaning Rank favorable countries considering safety of investment | Jency
Documentation : 1 and 2 | Tu
Documentation : 3 and 4 | Prerak
Documentation : 5 and 6 | Jency
R Script Draft | Tu, Prerak, Jency
R Plot Draft Title, Labels, details, a key, extra point for the team | Tu, Prerak
R plot Draft Description of the plot | Jency
Presentation | Tu, Prerak, Jency
Git Package : 1 and 2 | Tu
Git Package : 3 | Prerak
Git Package : 4 and 5 | Jency